WORLD ASSOCIATION OF AZERBAIJANI SCIENTISTS

Forum 2024

Strategic Implementation Framework

━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━

From roadmap themes to implementable projects,
action plans, and measurable national impact

Document type: Institutional strategic implementation plan

Version: 1.0 — May 2026

Status: Working framework for leadership review

Classification: Internal / partner shareable

# Table of contents

After opening in Microsoft Word, click the table below, press F9, or right-click → Update Field → Update entire table to refresh page numbers.

Table of contents	2

Executive summary	4

1. Purpose, scope, and alignment	4

1.1 Purpose	4

1.2 Scope	4

1.3 Alignment with WAAS mission and scientific diplomacy	4

2. Methodology and evidence base	5

2.1 Sources synthesised	5

2.2 Consolidation principles	5

3. Governance and execution model	5

3.1 Recommended governance structure	5

3.2 Execution principles	6

3.3 WAAS coordination mechanisms	6

4. Thematic architecture	6

4.1 Domain map (consolidated)	7

5. Domain portfolios: themes → initiatives → projects	7

Domain I — Education & academic development	7

Domain II — Scientific research & publications	8

Domain III — Digital platforms & virtual infrastructure	9

Domain IV — International cooperation & diaspora integration	10

Domain V — Youth & public outreach	11

Domain VI — Health & biotechnology	12

Domain VII — Arts, language & cultural heritage	13

Domain VIII — Governance, policy & legal mechanisms	13

Domain IX — Energy, environment & regional development	14

6. Implementation priorities (portfolio view)	15

6.1 Tier 1 — Launch immediately (0–12 months)	15

6.2 Tier 2 — Prepare year 1, scale years 2–3	15

6.3 Tier 3 — Strategic horizon (years 3–5+)	15

7. Phased action plans	15

7.1 Short term (0–12 months)	15

7.2 Medium term (12–36 months)	16

7.3 Long term (36–60+ months)	16

8. Stakeholder responsibilities	16

9. Competency and expertise matrix	17

10. Expected outcomes and measurable impact	17

10.1 Strategic outcomes (5-year)	17

10.2 KPI framework (illustrative)	17

11. University and institutional collaboration models	18

12. International partnership potential	18

13. Digital platform and AI integration roadmap	18

14. Funding and grant directions	19

15. Mentorship and youth involvement	19

16. Risks, challenges, and mitigation	20

17. Recommendations for executive decision (next 90 days)	20

18. Presentation guidance by audience	20

Annex A — Master project register (abbreviated)	21

Annex B — Relationship to published roadmap	22

Document control	22

## Executive summary

The First Forum of Azerbaijani Scientists Living Abroad (Forum 2024) produced a consolidated strategic roadmap for the development of Azerbaijani science and education. Participant proposals were synthesised into nine thematic domains spanning education, research, digital infrastructure, diaspora integration, youth outreach, health and biotechnology, cultural heritage, governance, and regional development.

This document transforms those roadmap themes into an implementable portfolio: concrete projects, phased action plans, accountable stakeholder groups, WAAS coordination mechanisms, competency requirements, measurable outcomes, partnership channels, funding directions, and risk mitigation. It is intended not as a discussion summary, but as a realistic execution framework aligned with WAAS’s mission of mobilising diaspora scientific potential, strengthening institutional bridges, and advancing scientific diplomacy.

Strategic intent: Strengthen Azerbaijan’s integration into the global scientific arena; convert diaspora expertise into structured, measurable contributions to national priorities; and establish WAAS as a trusted coordinator between scientists abroad, universities, the State Committee on Diaspora Affairs, and the Ministry of Science and Education.

## 1. Purpose, scope, and alignment

### 1.1 Purpose

Translate Forum 2024 roadmap goals into operational projects with owners, timelines, and indicators.

Provide a single reference for WAAS leadership, university rectors, the Diaspora Committee, the Ministry of Science and Education, and international partners.

Distinguish conceptual directions (vision-level) from operational actions (delivery-level).

### 1.2 Scope

| In scope | Out of scope (unless commissioned separately) |
| --- | --- |
| Projects derivable from Forum 2024 roadmap and plenary themes | Detailed legal drafting of new legislation |
| WAAS-coordinated diaspora–institution programmes | Full capital investment business cases for energy infrastructure |
| Digital, education, research, and diplomacy initiatives | Replacement of state budget planning processes |

### 1.3 Alignment with WAAS mission and scientific diplomacy

Forum outcomes reinforce WAAS’s long-term role as:

Network hub — connecting 80+ countries’ Azerbaijani scientists with home institutions.

Knowledge broker — matching diaspora expertise to national research and education priorities.

Scientific diplomacy channel — presenting evidence-based narratives (including Karabakh reconstruction and cultural heritage) through credible academic voices abroad.

Implementation partner — not duplicating state agencies, but coordinating diaspora participation in programmes led by universities, ANAS, the Diaspora Committee, and ministries.

Official forum messaging (Presidential appeal, Nobel laureate addresses, plenary theme on global academic networks) consistently emphasises: networking, institutional linkage, innovation, and youth. This framework mirrors those priorities.

## 2. Methodology and evidence base

### 2.1 Sources synthesised

| Source | Contribution |
| --- | --- |
| Published strategic roadmap (en/forum/2024/roadmap.html, Strateji_yol_xəritəsi.docx) | Nine thematic goal clusters |
| Forum programme and plenary minutes | Global academic network; diaspora–university linkage; international models |
| Participant presentations (e.g. bioinformatics/AI, education policy, regional development) | Domain-specific operational ideas |
| Diaspora Committee and institutional addresses | Karabakh communication, Azerbaijan Houses, education of new diaspora generation |
| WAAS cooperation documentation | Governance actors and partner institutions |

### 2.2 Consolidation principles

Merged overlapping initiatives (e.g. multiple “online platform” ideas → single Diaspora Knowledge & Collaboration Platform).

Grouped by thematic domain with cross-cutting tags (AI, diplomacy, publications).

Prioritised by feasibility, diaspora comparative advantage, and institutional dependency.

Phased into short (0–12 months), medium (12–36 months), and long (36–60+ months) horizons.

## 3. Governance and execution model

### 3.1 Recommended governance structure

┌─────────────────────────────────────────────────────────────┐
│  Strategic Steering Committee (SSC)                         │
│  WAAS Executive Board + invited: 2 rectors, Diaspora        │
│  Committee rep., Ministry liaison (observer)                │
└──────────────────────────┬──────────────────────────────────┘
                           │
┌──────────────────────────▼──────────────────────────────────┐
│  Implementation Secretariat (hosted by WAAS)                  │
│  Programme managers per domain; M&E officer; digital lead   │
└──────────────────────────┬──────────────────────────────────┘
                           │
        ┌──────────────────┼──────────────────┐
        ▼                  ▼                  ▼
   Domain Working      University          International
   Groups (DWGs)       Cluster Leads       Partner Desk

Strategic Steering Committee (SSC) — quarterly; approves portfolio, priorities, and major partnerships.

Implementation Secretariat — day-to-day coordination, reporting, grant pipeline support.

Domain Working Groups (DWGs) — thematic leads from WAAS membership; draft work plans; recruit experts.

University Cluster Leads — rotating rector/academic council nominees per project cluster.

International Partner Desk — ERASMUS/Horizon liaison, MOU tracking, embassy science attaché contact map.

### 3.2 Execution principles

| Principle | Application |
| --- | --- |
| WAAS coordinates, institutions deliver | WAAS does not replace universities or ministries; it mobilises diaspora input and tracks commitments. |
| Pilot → scale | Every major initiative starts as a 12-month pilot with explicit go/no-go criteria. |
| Open metrics | Annual public implementation report (aligned with roadmap page updates). |
| Ethics & integrity | Research ethics, authorship standards, and anti-plagiarism norms embedded in publication support programmes. |

### 3.3 WAAS coordination mechanisms

| Mechanism | Function |
| --- | --- |
| Forum Implementation Registry | Central register of projects, status, owners, KPIs (digital, maintained by Secretariat). |
| Scientist–Institution Matchmaking Service | Pairs diaspora experts to university/ANAS requests (building on existing WAAS directory). |
| Quarterly Implementation Forum (virtual) | Progress review; successor to ad-hoc post-Forum coordination. |
| Rector Roundtable (annual) | Aligns university clusters with national priorities; co-chaired with Ministry observer. |
| Grant Support Unit | Templates, partner finding, proposal clinics for Horizon Europe, ERASMUS+, bilateral funds. |
| Working Groups on AI & Bioinformatics | Cross-domain technical council (see Domain I). |

## 4. Thematic architecture

Nine forum roadmap domains are retained, with three cross-cutting lenses:

| Cross-cutting lens | Applies across |
| --- | --- |
| A. Artificial intelligence & data science | Digital infrastructure, health/biotech, research, education |
| B. Scientific diplomacy & narrative integrity | International cooperation, culture, Karabakh/regional development |
| C. Diaspora network capital | All domains — mobility, mentoring, joint appointments |

### 4.1 Domain map (consolidated)

| ID | Domain | Forum roadmap anchor | Priority tier* |
| --- | --- | --- | --- |
| I | Education & academic development | Joint degrees, exchanges, regional faculties | P1 |
| II | Scientific research & publications | Scopus support, journals, thematic centres | P1 |
| III | Digital platforms & virtual infrastructure | Virtual university, databases, online certification | P1 |
| IV | International cooperation & diaspora integration | ERASMUS/Horizon, recognition, visits | P1 |
| V | Youth & public outreach | School talks, mentoring, science motivation | P2 |
| VI | Health & biotechnology | Bioinformatics centres, medical databases, fellowships | P2 |
| VII | Arts, language & cultural heritage | Music, toponymy, migration encyclopaedias | P2 |
| VIII | Governance, policy & legal mechanisms | PhD reform, diploma recognition, policy papers | P2 |
| IX | Energy, environment & regional development | Green energy, Karabakh models, agrotourism | P3 |

\*P1 = launch within 12 months; P2 = prepare in year 1, scale in years 2–3; P3 = strategic alignment, phased after core network is operational.

## 5. Domain portfolios: themes → initiatives → projects

Each project includes: code, description, lead stakeholder group, WAAS role, horizon, and primary KPI.

### Domain I — Education & academic development

Strategic theme: Internationalise Azerbaijani higher education through structured diaspora academic participation.

| Initiative | Projects (consolidated) | Lead stakeholders | WAAS role | Horizon |
| --- | --- | --- | --- | --- |
| I-A. Joint & staged degree pathways | I-A1 Dual-degree pilot with 2 EU + 1 Turkish partner universities I-A2 Staged PhD pathway (coursework abroad / dissertation home) I-A3 Work-integrated learning (WIL) module catalogue | Rectors’ Council; Ministry | Matchmaking; MOU facilitation; diaspora faculty roster | S: pilots; M: scale |
| I-B. Intensive schools & certification | I-B1 Annual Summer/Winter Diaspora Science School (rotating host university) I-B2 Micro-credential framework (transliteration, research methods, grant writing) | Host universities; WAAS DWG Education | Curriculum co-design; expert recruitment | S |
| I-C. Regional academic capacity | I-C1 Feasibility for regional faculties/centres (2 priority regions) I-C2 Translation methodology certificate for graduate students | Ministry; local executive authorities | Expert panels; policy brief | M–L |

Key competencies: Curriculum design, accreditation standards, international QA, Azerbaijani/English academic writing.

Expected outcomes: ≥3 formal dual-degree or exchange MOUs; ≥200 students in intensive schools by year 3; measurable rise in co-authored papers with diaspora affiliations.

### Domain II — Scientific research & publications

Strategic theme: Raise international visibility and quality of Azerbaijani research output.

| Initiative | Projects | Lead stakeholders | WAAS role | Horizon |
| --- | --- | --- | --- | --- |
| II-A. Publication excellence | II-A1 Scopus publication support programme (mentoring + APC guidance) II-A2 Launch planning for 1–2 internationally indexed Azerbaijani journals (English + AZ) | ANAS; universities; library consortia | Mentor network; ethics guidelines | S–M |
| II-B. Thematic research centres | II-B1 Toponymy & migration history centre (virtual + ANAS link) II-B2 Karabakh University–linked interdisciplinary centre (reconstruction, environment, social studies) | Karabakh University; ANAS | Diaspora senior fellows; seminar series | M |
| II-C. Scholarly editions | II-C1 Regional anthology series (e.g. Borchali) — merged literary projects II-C2 National encyclopaedia of migration heritage (digital-first) | Cultural institutions; publishers | Editorial board diaspora participation | M–L |

Key competencies: Bibliometrics, journal editing, peer review, digital humanities, open access policy.

Expected outcomes: 15% increase in Scopus-indexed articles from participating units (baseline TBD); 1 journal indexed or accepted for evaluation within 36 months.

### Domain III — Digital platforms & virtual infrastructure

Strategic theme: Create persistent digital infrastructure for diaspora–home knowledge exchange.

| Initiative | Projects | Lead stakeholders | WAAS role | Horizon |
| --- | --- | --- | --- | --- |
| III-A. Diaspora Knowledge & Collaboration Platform (DKCP) | III-A1 Scientist directory upgrade (skills tags, availability, languages) III-A2 Project board (institutions post needs; scientists respond) III-A3 Document repository & best-practice library | WAAS (host); Ministry observer | Platform owner & operator | S |
| III-B. Virtual learning layer | III-B1 WAAS Open Course channel (curated MOOCs + forum lectures) III-B2 Online certification system (linked to I-B2 micro-credentials) III-B3 YouTube/social science communication series (“Science for Azerbaijan”) | Universities; media partners | Content curation; quality standards | S–M |
| III-C. Virtual university consortium | III-C1 Consortium MOU (5 universities + WAAS) III-C2 Shared digital campus pilot (10 cross-listed modules) | Rectors’ Council | Secretariat; technical RFP | M |

AI integration (cross-cutting): DKCP to include AI-assisted expert matching (with human validation); automated translation support for AZ/EN/RU content; responsible-use policy for generative AI in course materials.

Key competencies: EdTech, LMS integration, cybersecurity, data governance, UX, AI/ML engineering.

Expected outcomes: ≥500 active scientist profiles with collaboration flags; ≥1,000 course completions/year by year 3; platform uptime ≥99%.

### Domain IV — International cooperation & diaspora integration

Strategic theme: Embed Azerbaijani diaspora scientists in global programmes and institutional partnerships.

| Initiative | Projects | Lead stakeholders | WAAS role | Horizon |
| --- | --- | --- | --- | --- |
| IV-A. Grant & mobility pipeline | IV-A1 ERASMUS+ & Horizon Europe helpdesk (monthly clinics) IV-A2 Bilateral mobility fund mapping (30+ countries) IV-A3 “Return & contribute” visiting scientist scheme (3–6 month placements) | Ministry; universities; embassies | Grant Support Unit; scientist matching | S |
| IV-B. Diaspora organisation network | IV-B1 Formal cooperation with Azerbaijan Houses (30 locations) for science events IV-B2 Annual diaspora science delegation to Baku (linked to Forum 2.0) | Diaspora Committee | Co-organiser; programme design | S (annual) |
| IV-C. Language & literature abroad | IV-C1 Azerbaijani language lectureships — pilot 5 universities IV-C2 Student–scientist mutual visit fund (seed grants) | Ministry; MFA cultural attachés | Expert deployment lists | M |

Scientific diplomacy: Position WAAS voices in international conferences on Karabakh reconstruction, energy transition, and Turkic studies — with fact-based briefing packs (coordinated with Domain VII and IX).

Key competencies: EU programme administration, international law (mobility), cultural diplomacy, public communication.

Expected outcomes: ≥20 successful grant applications supported/year; ≥50 bilateral visits/year by year 3.

### Domain V — Youth & public outreach

Strategic theme: Inspire next-generation STEM and humanities engagement.

| Initiative | Projects | Lead stakeholders | WAAS role | Horizon |
| --- | --- | --- | --- | --- |
| V-A. Schools & universities outreach | V-A1 “Scientist in the Classroom” diaspora speaker bureau V-A2 Regional science fair mentorship (pilot 3 cities) | Ministry (schools); universities | Speaker roster; training | S |
| V-B. Mentoring programmes | V-B1 Diaspora–student mentoring platform (1:1 and group) V-B2 Early-career researcher mentoring (grant & publication focus) | Universities; WAAS | Platform module; mentor certification | S–M |
| V-C. Public science | V-C1 Annual youth science camp (hybrid) | Host university | Programme committee | M |

Key competencies: Pedagogy, youth safeguarding, science communication, mentoring supervision.

Expected outcomes: ≥100 school events/year; ≥300 active mentor–mentee pairs by year 2.

### Domain VI — Health & biotechnology

Strategic theme: Build computational biology and medical research capacity (forum emphasis: bioinformatics, genetic research, medical databases).

| Initiative | Projects | Lead stakeholders | WAAS role | Horizon |
| --- | --- | --- | --- | --- |
| VI-A. Bioinformatics & AI in life sciences | VI-A1 National bioinformatics centre planning group (ANAS + 2 universities) VI-A2 Joint lab placements abroad for early-career bioinformaticians VI-A3 Multi-omics training workshop series (based on Forum presentation themes) | ANAS; medical universities; diaspora labs (US/EU) | Expert recruitment; curriculum | M |
| VI-B. Medical knowledge infrastructure | VI-B1 Azerbaijani clinical research registry (pilot disease areas) VI-B2 Physician–researcher fellowship exchange | Ministry of Health; hospitals | Advisory diaspora clinicians | M–L |
| VI-C. Biotechnology translation | VI-C1 Innovation bridge for med-tech patents (link to II-A patenting) | Tech parks; ANAS | Scout diaspora entrepreneurs | L |

Key competencies: Bioinformatics, genomics, clinical trial design, medical ethics, HPC.

Expected outcomes: Centre feasibility approved; ≥30 fellows trained in bioinformatics by year 3; registry pilot live.

### Domain VII — Arts, language & cultural heritage

Strategic theme: Project Azerbaijani culture and historical scholarship internationally.

| Initiative | Projects | Lead stakeholders | WAAS role | Horizon |
| --- | --- | --- | --- | --- |
| VII-A. Music & arts diplomacy | VII-A1 Digital archive of Azerbaijani composers (performances + scores) VII-A2 International concert/lecture series via Azerbaijan Houses | Ministry of Culture; conservatories | Diaspora artists network | M |
| VII-B. Humanities scholarship | VII-B1 Turkic toponymy research programme (merged with II-B1) VII-B2 Translation & publication of Azerbaijani literature abroad | Publishers; universities | Editor diaspora pool | M–L |
| VII-C. Migration heritage | VII-C1 Digital encyclopaedia of migration heritage (linked to II-C2) | ANAS; libraries | Editorial coordination | L |

Key competencies: Musicology, literary translation, historical linguistics, digital archiving.

Expected outcomes: Archive ≥500 works indexed; ≥10 international cultural events/year.

### Domain VIII — Governance, policy & legal mechanisms

Strategic theme: Strengthen systemic enablers for science and education reform.

| Initiative | Projects | Lead stakeholders | WAAS role | Horizon |
| --- | --- | --- | --- | --- |
| VIII-A. Policy intelligence | VIII-A1 Annual “State of Diaspora Science” policy paper VIII-A2 PhD supervision reform recommendations (international benchmarking) | Ministry; ANAS | Author diaspora experts | S (annual) |
| VIII-B. Recognition & mobility law | VIII-B1 Diploma recognition fast-track study (comparative law) VIII-B2 Model MOU clauses for joint appointments | Ministry; universities | Legal expert group | M |
| VIII-C. Strategic planning support | VIII-C1 University internationalisation maturity assessments | Rectors’ Council | Assessment tool + peer review | M |

Key competencies: Higher education policy, comparative law, quality assurance, statistics.

Expected outcomes: Policy paper adopted for consultation; recognition study delivered to Ministry.

### Domain IX — Energy, environment & regional development

Strategic theme: Apply science to green transition and liberated territories’ development.

| Initiative | Projects | Lead stakeholders | WAAS role | Horizon |
| --- | --- | --- | --- | --- |
| IX-A. Green energy & digital utilities | IX-A1 Solar/agrotourism feasibility pilots (2 districts) IX-A2 Digital solutions for power-station efficiency (PoC with utility partner) | Energy Ministry; local authorities | Diaspora engineers | M–L |
| IX-B. Karabakh & regional models | IX-B1 Interdisciplinary Karabakh development science panel IX-B2 Environmental monitoring knowledge exchange | Karabakh University; state agencies | Scientific diplomacy briefings | M |
| IX-C. Sustainable regional planning | IX-C1 Natural-resource-based development templates for regions | Planning authorities | Expert workshops | L |

Key competencies: Renewable energy, environmental science, GIS, regional economics.

Expected outcomes: 2 pilot studies completed; annual Karabakh science panel established.

## 6. Implementation priorities (portfolio view)

### 6.1 Tier 1 — Launch immediately (0–12 months)

| Code | Project | Rationale |
| --- | --- | --- |
| III-A1–A3 | Diaspora Knowledge & Collaboration Platform | Enables all other domains; builds on existing WAAS website/directory |
| IV-A1 | Grant helpdesk | High diaspora demand; low capital requirement |
| I-B1 | Diaspora Science School | Visible outcome; rector buy-in from Forum |
| V-B1 | Mentoring platform | Strong forum consensus; youth pipeline |
| II-A1 | Scopus support programme | Direct research impact |
| VIII-A1 | Annual policy paper | Positions WAAS as policy partner |

### 6.2 Tier 2 — Prepare year 1, scale years 2–3

| Code | Project |
| --- | --- |
| I-A1 | Dual-degree pilot |
| III-C1 | Virtual university consortium |
| VI-A1 | Bioinformatics centre planning |
| II-B2 | Karabakh-linked research centre |
| VII-A1 | Composers digital archive |

### 6.3 Tier 3 — Strategic horizon (years 3–5+)

| Code | Project |
| --- | --- |
| II-C2 | Migration heritage encyclopaedia |
| IX-C1 | Regional development templates |
| VI-C1 | Med-tech innovation bridge |

## 7. Phased action plans

### 7.1 Short term (0–12 months)

| Quarter | Actions |
| --- | --- |
| Q1 | Establish SSC and Secretariat; approve Tier 1 portfolio; DKCP requirements & vendor selection |
| Q2 | Launch DKCP beta; first Grant Helpdesk cycle; Mentoring platform pilot (50 pairs) |
| Q3 | Diaspora Science School #1; Scopus mentoring cohort #1; Schools speaker bureau (20 events) |
| Q4 | Annual policy paper published; Forum Implementation Report; plan Forum 2.0 |

### 7.2 Medium term (12–36 months)

Scale DKCP to full membership; virtual university consortium MOU signed.

3+ dual-degree or exchange agreements operational.

Bioinformatics centre business case approved; Karabakh centre staffed with diaspora affiliates.

Journal launch pathway completed; first impact factors tracked.

### 7.3 Long term (36–60+ months)

Self-sustaining mix of grant income, institutional co-funding, and membership dues.

WAAS recognised as standing diaspora science interface in national education/science strategies.

Measurable shift in international co-authorship, student mobility, and indexed publications.

## 8. Stakeholder responsibilities

| Stakeholder | Primary responsibilities | Interface with WAAS |
| --- | --- | --- |
| WAAS Executive Board | Strategic approval, representation, fundraising advocacy | SSC chair |
| WAAS Secretariat / DWGs | Delivery coordination, expert mobilisation | Day-to-day |
| University rectors | Host pilots, credit recognition, faculty co-appointment | Cluster leads |
| ANAS | Research centres, journals, humanities programmes | MOU partner |
| Ministry of Science and Education | Policy alignment, accreditation, national programmes | Observer on SSC; co-signalling |
| State Committee on Diaspora Affairs | Azerbaijan Houses, Karabakh narrative, diaspora events | Co-organiser IV-B |
| Karabakh University | Regional research anchor, field programmes | II-B2, IX-B |
| International partners (EU, Türkiye, etc.) | Mobility, grants, joint labs | IV-A |
| Diaspora scientists (WAAS members) | Expertise, mentoring, joint publications | All domains |

## 9. Competency and expertise matrix

| Domain | Essential expertise | Sourcing |
| --- | --- | --- |
| I Education | Academic QA, internationalisation | Diaspora professors; EU university partners |
| II Research | Bibliometrics, editing, peer review | Senior researchers abroad |
| III Digital | EdTech, full-stack, data governance | Tech diaspora; vendor partners |
| IV International | EU programmes, diplomacy | Grant specialists; embassies |
| V Youth | Pedagogy, safeguarding | Younger diaspora scientists |
| VI Health | Bioinformatics, clinical research | Forum presenters’ networks (e.g. US/EU labs) |
| VII Culture | Humanities, musicology, translation | Cultural diaspora organisations |
| VIII Governance | Policy, law | Policy institutes; legal academics |
| IX Energy/region | Engineering, environmental science | Industry diaspora |

Gap mitigation: Competency gaps filled via pro bono expert registry on DKCP, short-term consultancy grants, and twinning with foreign departments.

## 10. Expected outcomes and measurable impact

### 10.1 Strategic outcomes (5-year)

Integrated diaspora–home science system with digital infrastructure and recurring Forum rhythm.

Higher international research visibility for Azerbaijani institutions.

Expanded youth pipeline into STEM and research careers.

Stronger scientific diplomacy capacity on priority narratives.

Sustainable WAAS institutional model beyond volunteer core.

### 10.2 KPI framework (illustrative)

| KPI | Baseline | Year 1 target | Year 3 target |
| --- | --- | --- | --- |
| Active DKCP scientist profiles | ~80 (members) | 200 | 500 |
| Grant applications supported | 0 (structured) | 15 | 60 cumulative |
| Mentoring pairs active | 0 | 50 | 300 |
| Scopus mentoring publications | TBD | +10 articles | +50 articles |
| School outreach events | 0 | 20 | 100 cumulative |
| Dual-degree/MOU agreements | 0 new (post-Forum) | 1 | 3+ |
| MOOC/certification completions | 0 | 200 | 1,000 |
| Policy papers adopted for consultation | 0 | 1 | 3 |
| International cultural/science events | ad hoc | 5 | 15/year |

Baselines to be confirmed with Ministry and ANAS in Q1.

## 11. University and institutional collaboration models

| Model | Description | Example project |
| --- | --- | --- |
| Twinning department | AZ department paired with diaspora-led department abroad | VI-A2 placements |
| Joint appointment | Fractional appointments for diaspora professors | I-A1 dual supervision |
| Consortium MOU | Multi-university digital campus | III-C |
| Science embassy desk | Scientist liaison at Azerbaijan House | IV-B1 |
| Living lab | Regional pilot (energy, agrotourism) | IX-A1 |

Rector engagement package: Annual roundtable + written commitment template (host one pilot, nominate cluster lead, provide in-kind logistics).

## 12. International partnership potential

| Partner type | Opportunity | Projects |
| --- | --- | --- |
| EU universities | ERASMUS+, Horizon Europe, dual degrees | I-A, IV-A |
| Turkish universities | Turkic studies, engineering, cultural programmes | I, VII |
| US national labs / institutes | Bioinformatics, AI, energy | VI-A, III AI |
| UNESCO / cultural agencies | Heritage, music archive | VII |
| Diaspora professional associations | Mentoring, speaker bureau | V |
| Corporate R&D (pharma, energy) | Fellowships, innovation bridge | VI-C, IX |

China diaspora model (plenary reference): Study structured diaspora engagement; adapt elements via IV-B without copying governance model wholesale.

## 13. Digital platform and AI integration roadmap

| Phase | Deliverable |
| --- | --- |
| Phase 1 (S) | DKCP v1: directory, project board, document library |
| Phase 2 (S–M) | LMS integration; certification tracking; WAAS Open Course |
| Phase 3 (M) | AI-assisted expert matching (validated recommendations) |
| Phase 4 (M–L) | Multi-omics / research data sandbox (ethics-approved subset) |
| Governance | AI ethics charter; data residency policy; bilingual UX (AZ/EN) |

Forum presentations explicitly linked bioinformatics, artificial intelligence, and national scientific potential — VI-A and III are the primary carriers.

## 14. Funding and grant directions

| Source | Fit | Projects |
| --- | --- | --- |
| Horizon Europe | Research, innovation, mobility | II, IV, VI |
| ERASMUS+ | Higher education cooperation | I, IV |
| Bilateral science funds (e.g. DAAD, TÜBİTAK, NSF partnerships) | Exchanges, workshops | I-B, VI-A2 |
| Diaspora Committee / state programmes | Events, Azerbaijan Houses, Karabakh | IV-B, VII, IX |
| University in-kind | Venues, credits, faculty time | All pilots |
| WAAS membership & donations | Secretariat, platform OPEX | III-A |
| Corporate CSR | Youth, digital skills | V, III-B |
| Foundation grants | Culture, humanities | VII |

Grant Support Unit deliverables: Call calendar; template library; partner finder; monthly proposal clinic; success-case repository on DKCP.

## 15. Mentorship and youth involvement

Consolidated Diaspora Science Mentoring System (DSMS) — merges V-B1, V-B2, and elements of II-A1:

| Track | Audience | Content |
| --- | --- | --- |
| School track | Grades 9–11 | Career talks; science clubs |
| Undergraduate track | BA/BSc | Research skills; summer lab placement |
| Early-career track | MSc/PhD/postdoc | Publications; grants; ethics |

Safeguarding: Background checks for school-facing mentors; code of conduct; data protection on platform.

Youth leadership: “Young WAAS Associates” programme — students co-organise outreach under senior mentor supervision.

## 16. Risks, challenges, and mitigation

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Institutional fragmentation | Duplication, slow MOUs | SSC + single Implementation Registry |
| Volunteer burnout | Delivery delays | Paid Secretariat core (even 2–3 FTE); rotate DWG chairs |
| Low follow-through post-Forum | Credibility loss | Quarterly virtual forum; public KPI report |
| Funding gaps | Pilot stall | Tiered portfolio; grant unit; in-kind university model |
| Digital platform underuse | Wasted investment | Co-design with scientists; integrate with grant & mentoring workflows |
| Political sensitivity (diplomacy narratives) | Reputational risk | Peer-reviewed briefs; academic tone; SSC clearance for external statements |
| Quality concerns in publication support | Ethics issues | Mentoring standards; plagiarism training; no ghost-writing |
| Brain drain perception | Domestic resistance | Emphasise “return & contribute” placements and joint appointments |
| AI misuse | Misinformation, privacy | AI ethics charter; human-in-the-loop matching |

## 17. Recommendations for executive decision (next 90 days)

Approve this framework as WAAS’s official Forum 2024 implementation reference.

Constitute the Strategic Steering Committee and name Domain Working Group chairs.

Fund DKCP Phase 1 and Secretariat minimum staffing (grant or diaspora sponsorship).

Sign a trilateral letter of intent with one ministry and Diaspora Committee referencing shared KPIs.

Announce Tier 1 pilots at a rector roundtable; request written host commitments.

Schedule Forum 2.0 (2026 or 2027) as implementation review milestone.

Publish annual implementation report on WAAS website (linked from roadmap page).

## 18. Presentation guidance by audience

| Audience | Emphasise | De-emphasise |
| --- | --- | --- |
| WAAS leadership | Governance, Secretariat, Tier 1 funding, KPI accountability | Technical platform details |
| University rectors | Dual degrees, virtual consortium, in-kind pilots, cluster leads | Diaspora politics |
| Diaspora Committee | Azerbaijan Houses, Karabakh panel, scientific diplomacy | Internal WAAS admin |
| Ministry of Science and Education | Policy papers, PhD reform, accreditation, grant pipeline | Cultural projects (brief only) |
| International partners | Horizon/ERASMUS, bioinformatics, joint labs, MOUs | Domestic institutional politics |

## Annex A — Master project register (abbreviated)

| Code | Project name | Domain | Priority | Horizon |
| --- | --- | --- | --- | --- |
| III-A1–3 | Diaspora Knowledge & Collaboration Platform | III | P1 | S |
| IV-A1 | Grant & Horizon/ERASMUS helpdesk | IV | P1 | S |
| I-B1 | Diaspora Science School | I | P1 | S |
| V-B1 | Mentoring platform | V | P1 | S |
| II-A1 | Scopus publication support | II | P1 | S |
| VIII-A1 | Annual policy paper | VIII | P1 | S |
| I-A1 | Dual-degree pilot | I | P2 | M |
| III-C1 | Virtual university consortium | III | P2 | M |
| VI-A1 | Bioinformatics centre planning | VI | P2 | M |
| II-B2 | Karabakh-linked research centre | II | P2 | M |
| VII-A1 | Composers digital archive | VII | P2 | M |
| II-C2 | Migration heritage encyclopaedia | II/VII | P3 | L |
| IX-C1 | Regional development templates | IX | P3 | L |

Full operational charters for Tier 1 projects to be developed by Secretariat in Q1.

## Annex B — Relationship to published roadmap

This framework implements the public strategic roadmap at:

English: /en/forum/2024/roadmap.html

Azerbaijani: /az/forum/2024/roadmap.html

Recommended website enhancement: add a “Implementation” section linking to this document (or an executive summary page) after leadership approval.

## Document control

| Field | Value |
| --- | --- |
| Author | WAAS Forum Implementation Working Group (draft) |
| Reviewers | Executive Board (pending) |
| Next review | Upon SSC constitution |
| Classification | Internal / partner shareable |

End of document